Project Document Cover Sheet

| Project Information |
| --- |
| Project Acronym | VPMan |
| Project Title | Integrating VOMS and PERMIS for Superior Secure Grid Management |
| Start Date | 1 March 2007 | End Date | 31 July 2008 |
| Lead Institution | University of Kent |
| Project Director | Professor David Chadwick |
| Project Manager & contact details | Prof David Chadwick, University of Kent, Computing Laboratory, Canterbury, CT2 7NF. Email: d.w.chadwick@kent.ac.uk Mobile: +44 77 96 44 7184 |
| Partner Institutions | The National e-Science Centre (NeSC) at the University of Glasgow (http://www.nesc.ac.uk/) The National Grid Service at the Science and Technology Facilities Council (http://www.grid-support.ac.uk/) Open Middleware Infrastructure Institute UK (http://www.omii.ac.uk/) |
| Project Web URL | http://sec.cs.kent.ac.uk/vpman/ |
| Programme Name (and number) | e-Infrastructure (security) |
| Programme Manager | James Farnhill |

| Document Name |
| --- |
| Document Title | Project Plan |
| Reporting Period |  |
| Author(s) & project role | D Chadwick, Project Director |
| Date | 27 October 2007 | Filename | project_plan.doc |
| URL | http://sec.cs.kent.ac.uk/vpman/project_plan.doc |
| Access | ( Project and JISC internal | ( General dissemination |

| Document History |
| --- |
| Version | Date | Comments |
| 0.9 | 14 July 2007 | First draft for circulation to project team |
| 1.0 | 28 July 07 | First complete version incorporating feedback from JISC and project partners |
| 1.01 | 13 August 07 | Minor changes from partners |
| 1.02 | 27 Oct. 07 | Added that CA had been signed off. Replaced Bassem Nasser with other staff. Added a new deliverable D1.3 |

# JISC Project Plan

## Overview of Project

### 1. Background

Managing grids from a security perspective comprises two main functions: the privilege assignment function in which users are assigned to roles, and the authorisation decision function in which policies are set for which roles should have access to which grid resources. These functions typically take place in different systems at different locations. These functions are carried out by the Identity Provider (IdP) and Service Provider (SP) in Shibboleth terminology, and by the VO Manager and grid service provider in grid terminology. More generally, privileges are assigned to users as a mixture of attributes and roles, by one or more attribute authorities (AAs). Attributes (such as login id and department) are assigned by a user’s home institution; virtual organisation (VO) roles are assigned by a VO management authority, and professional memberships by learned societies such as IEEE and ACM. These attributes are then transferred to the grid SP, where the authorisation decision function is carried out based on the policy set by the resource’s owner. If a user’s grid job is accessing multiple resources at multiple sites, then the authorisation decision function may take place several times at several different resource sites using different policies in each case. The Virtual Organisation Management Service (VOMS) [1] provides a well utilised privilege assignment function which is carried out by the VO manager. It is the chosen VO management function of Grid projects such as EGEE, and it is planned to integrate it into the National Grid Service (NGS) at CCLRC. However, its authorisation decision function is intentionally missing by design (it relies on LCAS and other plug-ins). PERMIS on the other hand provides a feature rich, modular authorisation decision function, with a user friendly policy management interface, is already integrated into Shibboleth and is currently being integrated into the OMII-UK software environment by the London E-Science Centre (LESC). However, it has a less well developed privilege assignment function. This project proposes to integrate the privilege assignment function of VOMS with the authorisation decision function of PERMIS, so that the management of grids becomes easier, whilst simultaneously allowing finer grained more feature rich authorisation infrastructures to be designed and built. We expect the combination of these technologies to have a significant impact across the UK and international e-Science communities.

### 2. Aims and Objectives

The project objectives are to:

- integrate VOMS and PERMIS, more specifically the VOMS user management and attribute assignment function with the PERMIS policy based authorisation decision function;

- ensure they seamlessly inter-work with the latest Grid technologies including Globus Toolkit version 4 (GT4), the Open Middleware Infrastructure Institute UK (OMII-UK) and Shibboleth;

- validate the results in several representative major pilot applications run by the NeSC;

- evaluate the combined software from user, administrator and Grid developer perspectives;

- integrate the combined infrastructure with the National Grid Service (NGS) at CCLRC;

- distribute the integrated software as open source code as part of either Globus Toolkit, the OMII-UK repository, or the US-NMI, or a combination of them.

### 3. Overall Approach

NGS, OMII and NeSC will provide use cases that are to be supported

Kent will analyse the existing technologies and then produce a design for the integrated infrastructure. NGS, OMII and NeSC will provide feedback and QA of the design.

Kent will implement the design, producing the software glue for VOMS and PERMIS, and the policy management GUI to support VOMS attributes.

NeSC will build the testbeds for piloting the integrated software in various configurations with different grid applications.

OMII will provide help and support with the integration with their middleware and packaging of the final release.

NGS will provide help and support with integrating the piloted software into their operational services

### 4. Project Outputs

D1.1 A document describing the background to the integration work.

D1.2 A document of case studies to be supported

D2.1 A VOMS-PERMIS integration design document.

D3.1 A modified PERMIS Policy Editor and Wizard with documentation and help files

D4.1 Beta software ready for validation and piloting.

D4.2 Preparation of test bed, services and portals

D5.1 A paper for an international grid conference describing the piloting of the integrated VOMS-PERMIS software with GT4 and/or OMII-UK.

D5.2 A paper for an international grid conference describing the piloting of the integrated authorization software utilizing Shibboleth and multiple Grid middleware (GT4 and OMII-UK) including how user single sign-on across a range of UK e-Science resources can be supported with fine grained authorisation.

D5.3 Document describing the overall lessons learned in supporting this infrastructure from a user, an administrator and a Grid developer perspective

D6.1 The integrated software packaged with GT4 and OMII-UK and fully integrated into the NGS

D6.2. User, developer and administrator documentation for the integrated VOMS-PERMIS package including support in a Shibboleth-enabled environment, with guidance to Grid Operations Support Centre on practicalities of usage

D6.3 Final report to JISC

### 5. Project Outcomes

The project will allow grid administrators to gain more fine grained control over access to their grid resources. It will distribute management of user roles to local VO managers, whilst leaving control of access to resources with the resource owners. The creation of more sophisticated access control policies will be achieved through the use of XML based policies that are directly interpreted by the policy decision points (PDPs). The XML policies will be easy to create via the PERMIS GUI that displays the policy back in natural language to the policy writer.

Currently there is much duplication of effort in grid projects when it comes to specifying and building access controls. This project should allow most (if not all) grid projects to use the same more comprehensive and fine grained policy driven access control mechanism, thereby reducing effort, whilst simultaneously increasing security.

### 6. Stakeholder Analysis

| Stakeholder | Interest / stake | Importance |
| --- | --- | --- |
| NGS | Using the project’s outputs in their service | Very high |
| OMII | Using the project’s outputs in their open source software | High |
| Globus development team | Using the project’s outputs in GT4 and its successors | High |
| VOMS development team | Ensuring their interfaces and specifications are usable by others | Medium |
| Kent | Lead developer | Very High |
| University of Glasgow (NeSC) | Application demonstrators | High |
| JISC | Funding Body | Medium |

### 7. Risk Analysis

| Risk | Probability (1-5) | Severity (1-5) | Score (P x S) | Action to Prevent/Manage Risk |
| --- | --- | --- | --- | --- |
| Staffing problems at Kent (e.g. RA leaves) | 3 | 3 | 9 | We have a team of people at Kent and therefore will have substitutes if the main RA leaves. |
| Staffing problems at Glasgow | 3 | 3 | 9 | RAs at Glasgow are both able to cover each others work. Also other RAs at Glasgow can support this project |
| Insufficient support from OMII and/or NGS | 1 | 5 | 5 | This would critically impact the project, but given that both parties are stakeholders, the probability is low |
| Poor PM liaison between Kent and Glasgow | 1 | 3 | 3 | This would impact the ability to effectively pilot the results. Ensure frequent dialogue and early notification of problems. |
| Failure to find appropriate technical solution. | 1 | 3 | 3 | We do not believe there will be any significant technical problems with this project, but if there are we will almost certainly be able to build workarounds. |
| LESC integrating PERMIS into OMII-UK | 2 | 5 | 10 | Whilst the basic integration is already done, LESC are integrating Bouncy Castle ASN.1 handling and this is the risky. If this is unsuccessful we will have to fallback to IAIK binary libraries. |
| OGF completing the specification of the 2nd generation OGSA AuthZ protocols and on OMII-UK implementing them | 2 | 5 | 10 | As the PI is joint chair of the OGSA AuthZ WG and joint editor of the 2nd generation AuthZ profiles he can have some influence over their timely production. As Prof Sinnott is a member of the OMII-UK Users’ Forum the requirement has already been fed into OMII-UK. If OMII-UK do not implement (or subcontract) the 2nd generation protocol in time, we can still perform the OMII-UK demonstrator using the existing 1st generation protocol, but this will mean that some authorisation policies cannot be tested (i.e. ones that have conditions on operation arguments). |
| Failure of INFN, who is the main external supplier, to provide the VOMS SAML interface on time | 3 | 3 | 9 | A failure of this would compromise the pull model from working satisfactorily. Mitigating Action. Keep good communication channels open with them. Have flexible project planning |
| Legal issues with code | 1 | 1 | 1 | Make sure everything is BSD-like open source |
| Data Corruption/Hardware malfunction | 1 | 5 | 5 | Use versioning system and regular backups |
| Unrealistic scenarios/user cases | 3 | 3 | 9 | We will use case studies from engineering domain (nanoCMOS) and clinical trials domain (VOTES) which are both major UK pilot projects |
| Beating the March 2009 deadline | 1 | 5 | 5 | We have a 13.5 month project which we have scheduled over 17 months so as to build sufficient contingency into the plan. We still have 8 months after the scheduled completion date to beat the March 2009 deadline |
| Biased reporting of results | 1 | 3 | 3 | By having NeSC as the project partner responsible for the demonstrations, one can be assured that they will specifically feed the positive and negative results of the demonstrators into the UK e-Science and OMII-UK user groups. |
| Application specific solutions | 1 | 5 | 5 | Through the rich portfolio of application projects at NeSC, we will fully explore the VOMS-PERMIS software in a variety of applications and fully analyse it against existing solutions |

### 8. Standards

| Name of standard or specification | Version | Notes |
| --- | --- | --- |
| X.509 proxy certificates | RFC 3820 | Use as is |
| X.509 attribute certificates | X.509 | Use VOMS variants |
| SAML (attribute assertions) | SAMLv1.1 or 2.0 | Use to pull attributes from a VOMS server |
| XACML (request context) | V2 | Use in GT4 to interface to PERMIS PDP |
| SAML (authz queries) | V1.1 | Use in OMII to interface to PERMIS |
| PERMIS XML policy schema (proprietary) | V10 | Use instead of XACML policies since easier to understand and faster to reach decision |

### 9. Technical Development

During the project all the software will be designed before any code is written. The designs will be quality assured by experienced staff and the project managers at each partner site.  All designs at Kent are held in a local Subversion SVN system for ease of distribution and tracking changes.

To ensure that the developers are using the most up-to-date code, and to make coherent and retractable changes to it, the CVS versioning system will be used. All the core PERMIS software is already held in this system.  The CVS content is frequently backed up onto a second hard disk, and a quarterly back-up is burnt onto a CD-RW. This protects the development process against hardware failure.

Any changes to the existing PERMIS codebase will be regression tested to ensure that no bugs are introduced. An automated regression testing facility has been developed for PERMIS containing a test suite with well over a 1000 test cases. New test cases are continually being added. All new functionality produced under this project will have regression tests developed for it. This will ensure that any future development will remain compatible with the ones developed under VPMan.

### 10. Intellectual Property Rights

Any IPR developed under this project will be owned by the University of Kent, but will be made freely available to the community through the release of open source software with a BSD-like license.

Any other third party software that will be used will also be open source with a zero cost license so that no encumbrances will be places on users of the project deliverables.

## Project Resources

### 11. Project Partners

Primary Contractor: University of Kent

Main Contact: Professor David Chadwick, University of Kent, Computing Laboratory

Fax +44 1227 762 811

Mobile: +44 77 96 44 7184

Email: D.W.Chadwick@kent.ac.uk

Project Partner: National Grid Centre, University of Glasgow

Main Contact: Professor Richard Sinnott, University of Glasgow

Email: r.sinnott@nesc.gla.ac.uk

Tel: 0141-330-8606

Fax: 0141-330-8625

Project Partner: National Grid Service

Main Contact: Dr Andrew Richards, National Grid Service

Email: a.j.richards@rl.ac.uk

Tel: 01235 778029

Fax: 01235 445945

Project Partner: OMII-UK

Main Contact: Mr Tim Parkinson,  OMII-UK

Email: tim.parkinson@soton.ac.uk

Tel: 02380 598382

Fax: 02380 598870

Consortium Agreement

A copy of an existing CA was provided by the NGS, and modified to suit the VPMan project. It was signed by all partners in Sept 2007

### 12. Project Management

Project Management will follow simplified PRINCE(2) principles.

The Project Board will comprise the nominees from each partner organisation (Kent, Glasgow, NGS, OMII-UK) plus the project manager and a member of JISC. The Project Board will meet quarterly to review progress and to authorise the next quarter’s planned work. The Project Board will also meet if an Exception Report is created by any of the site nominees indicating that the current work cannot be completed as planned. The Project Board will determine the best course of action in this event.

Technical day to day decisions will be made by the project manager and the development staff concerned, with reference to their site leaders where necessary. Important issues and exceptions will be reported to the site nominees. Strategic decision making will be made by the Project Manager in consultation with the Project Director.

The overall project director will be Professor David Chadwick from the University of Kent. He will spend approx 10% of his time on this project overall.

Staff at Kent

David Chadwick, Project Director and Project Manager, will spend approx 10% of his time on the project.

Linying Su, RA, will spend 100% of his time on the project development and implementation.

Staff at Glasgow

Tom Doherty and David Martin, research associates, will both spend 50% of their time on the project in exploring the integrated VOMS-PERMIS software in the identified case studies.

Richard Sinnott, PI for Glasgow, will spend approx 10% of his time on the project in managing the work at Glasgow, i.e. validating the software in the case studies and co-ordinating efforts with Kent.

Staff at NGS

Neil Geddes and Andrew Richards will provide input for use cases and overall project direction as stakeholders. David Spence will provide expertise from the NGS to assist with deployment of the project outputs. The listed staff are all based at STFC-RAL

Staff at OMII-UK

Tim Parkinson, Project Manager will spend up to but no more than 5% of his time on project management (unfunded) and will allocate suitably qualified OMII-UK staff to the relevant work packages.

### 13. Programme Support

The project would like the support of the programme manager in facilitating links with other projects and with external bodies where this is appropriate.

### 14. Budget

See Appendix A. There are no changes at present to the one in the proposal.

## Detailed Project Planning

### 15. Work Packages

Appendix B contains a detailed description of the various work packages and deliverables, along with a Gantt chart.

### 16. Evaluation Plan

| Timing | Factor to Evaluate | Questions to Address | Method(s) | Measure of Success |
| --- | --- | --- | --- | --- |
| M7-8 | PERMIS Policy Editor (formative) | Will the policy editor allow resource owners to easily specify their chosen authorisation policies? | Testing with user groups | >95% of user are able to achieve their objectives |
| M9-13 | Software deliverables (formative) | Will the integrated PERMIS-VOMS software allow grid users to control access their resources? | Testing with user groups | >95% of user are able to achieve their objectives |
| M14-17 | Pilot NGS service (summative) | Will the PERMIS-VOMS software improve the NGS? | Questionnaire | 75% of users and adminstrators surveyed are satisfied or very satisfied with the new NGS |
| Year after completion | Take up of open source software (summative) | Is there take up by the community at large? | Count number of downloads | 200+ downloads in initial 12 months after release. |

### 17. Quality Plan

| Output and Timing | Quality criteria | QA method(s) | Evidence of compliance | Quality responsibilities | Quality tools (if applicable) |
| --- | --- | --- | --- | --- | --- |
| User Documentation M9-M13 | Fitness for purpose | Review and test by independent users e.g. students | Test report | Project Manager | Word processor |
| Dissemination papers M14-M15 | Leading edge | Review by external reviewers | Accepted for conference or journal | Authors of paper | Word processor |
| Design documentation M2-M6 | Fit for purpose | Internal reviews | Signed off by Project Director | Project Director | Word processor, SVN |
| Software deliverables M4-M13 | Performs as expected | Code inspections | Integrated into NGS and OMII-UK | Project Director | CVS, Regression test bench |
| Background info document M1-M5 | Comprehensive and clear | Review by project members | Accepted by project team for publication on project web site | Project Manager | Word processor |
| Use cases document M1-M5 | All possible configurations covered | Review by project members | Accepted by project team for publication on project web site | Project Manager | Word processor |

### 18. Dissemination Plan

| Timing | Dissemination Activity | Audience | Purpose | Key Message |
| --- | --- | --- | --- | --- |
| M1 | Web site | Global grid community | To raise awareness | Project objectives |
| M1-3 | Questionnaire | VOMS community | Raise awareness and capture requirements | Project has started. What are your requirements |
| M9-13 | Pilot the software in NeSC grid projects | NeSC grid users | Engage a few pilot users | Try out the new service |
| M14-17 | Newsletters, mailing lists, flysheet, web sites about NGS service | UK grid community | Engage the community | New VOMS-PERMIS NGS is available |
| M6-18 | Conference presentations | Conference attendees | To publicise the project and its results | A new security service is available |
| M6-18 | Demonstrations | Conference/OGF/AH /Workshop attendees | Promote the project | New service and software is available |
| M14-17 | Distribute via OMII-UK, US-NMI | Global grid community | Promote the project’s outputs | New VOMS-PERMIS open source software is available |

### 19. Exit and Sustainability Plans

| Project Outputs | Action for Take-up & Embedding | Action for Exit |
| --- | --- | --- |
| Software deliverables and associated documentation | 1. NGS to incorporate software into their ongoing service. 2. OMII-UK to incorporate software into their ongoing releases 3. GT4 to include the software in its core release 4. PERMIS site to continue distributing the software | Access. Have software available for download. Preservation. ?? Maintenance. See table below. IPR. None needed. All software will be open source BSD |
| Case studies and best practice examples, a “How To” document | Widely disseminate these at various web sites | Access. Have available on various web sites for download Preservation. ?? Maintenance. See table below IPR. Users should be given permission to copy for own use |

| Project Outputs | Why Sustainable | Scenarios for Taking Forward | Issues to Address |
| --- | --- | --- | --- |
| PERMIS software | Standards based, open source, application independent authz infrastructure, modular, extensible | 1. Encourage open source community to build around it 2. Further RTD grants to continue its development | 1. How to fund coordinator of this project 2. Finding appropriate calls for proposals |

## Appendix A. Project Budget

|  | March 07 | Apr 07– Mar 08 | Apr 08– Mar 09 | TOTAL £ |
| --- | --- | --- | --- | --- |
| Directly Incurred Staff at Kent |  |  |  |  |
| RA 13.5 months 100% full time | £3,231 | £39,552 | £1,552 | £44,336 |
| Non-Staff at Kent |  |  |  |  |
| Travel and expenses | £250 | £1,750 | £2,000 | £4,000 |
| Hardware/software | £0 | £1,500 | £0 | £1,500 |
| Other | £100 | £1,000 | £300 | £1,400 |
| Total Non-Staff (B) | £350 | £4,250 | £2,300 | £6,900 |
| Directly Incurred Total (A+B=C) | £3,581 | £43,802 | £3,852 | £51,235 |
| Directly Allocated |  |  |  |  |
| Staff Prof Chadwick | £853 | £10,442 | £3,596 | £14,891 |
| Estates | £481 | £5,768 | £456 | £6,705 |
| Directly Allocated Total (D) | £1,334 | £16,210 | £4,052 | £21,596 |
| Indirect Costs (E) | £2,426 | £29,108 | £2,304 | £33,838 |
| Total Project Cost Kent | £7,341 | £89,120 | £10,208 | £106,669 |
| Directly Incurred Staff at NESC |  |  |  |  |
| RA 9 months 80% full time | £1,325 | £16,368 | £5,680 | £23,373 |
| Non-Staff at NESC |  |  |  |  |
| Travel and expenses | £250 | £1,750 | £2,000 | £4,000 |
| Hardware/software | £1500 |  |  | £1,500 |
| Other | £400 | £1,200 | £400 | £2,000 |
| Total Non-Staff (B) | £2,150 | £2,950 | £2,400 | £7,500 |
| Directly Incurred Total (A+B=C) | £3,475 | £19,318 | £8,080 | £30,873 |
| Directly Allocated |  |  |  |  |
| Staff Prof Sinnott | £393 | £4,950 | £1,688 | £7,031 |
| Estates | £446 | £5,357 | £1,786 | £7,589 |
| Directly Allocated Total (D) | £839 | £10,307 | £3,474 | £14,620 |
| Indirect Costs (E) | £1,755 | £21,061 | £7,020 | £29,837 |
| Total Project Cost NESC | £6,069 | £50,686 | £18,574 | £75,330 |
| Directly Incurred Staff at NGS and OMII |  |  |  |  |
| RA 2.75 months @ £38Kpa NGS RA 2.75 months OMII |  | £5,554 £4,989 | £3,173 £2,851 | £8,727 £7,840 |
| Non-Staff at NGS and OMII |  |  |  |  |
| Travel and expenses NGS Travel and expenses OMII |  | £500 £500 | £250 £250 | £750 £750 |
| Total Non-Staff (B) |  | £1,000 | £500 | £1,500 |
| Directly Incurred Total (A+B=C) |  | £11,543 | £6,524 | £18,067 |
| Directly Allocated NGS OMII |  | £851 £3,070 | £486 £1,754 | £1,337 £4,824 |
| Indirect Costs (E) NGS OMII |  | £5,750 £6,225 | £3,286 £3,557 | £9,036 £9,782 |
| Total Project Cost NGS and OMII |  | £27,439 | £15,607 | £43,046 |
| Total Project Cost | £13,410 | £167,245 | £44,389 | £225,045 |
| Amount Requested from JISC | £10,728 | £111,845 | £23,026 | £145,599 |
| Institutional Contributions | £2,682 | £55,400 | £21,363 | £79,446 |
| Percentage Contributions over the life of the project |  | JISC 65 % | Partners 35% | Total 100% |

## Appendix B. WORK PACKAGES

| WORKPACKAGES | Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1: Requirements and information gathering |  | X | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |
| 2: VOMS-PERMIS Integration Design |  |  | X | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |
| 3: Modify the PERMIS Policy Editor and Wizard |  |  |  |  |  | X | X |  |  |  |  |  |  |  |  |  |  |  |
| 4: VOMS-PERMIS and Shibboleth Integration and Test-bed establishment |  |  |  |  | X | X | X | X | X |  |  |  |  |  |  |  |  |  |
| 5: Run the Demonstrators to validate the Integration in e-Science applications |  |  |  |  |  |  |  |  |  | X | X | X | X | X |  |  |  |  |
| 6: Dissemination |  | X | x | x | x | x | x | x | x | x | x | x | x | x | X | X | X | X |

Project start date: 1 March 2007

Project completion date: 31 July 2008

Duration: <nn> months

|  |  |  |  | Milestone | Responsibility |
| --- | --- | --- | --- | --- | --- |
| YEAR 1 |  |  |  |  |  |
| WORKPACKAGE 1: Objective: Requirements and information gathering | 1 March 2007 | 30 July 2007 |  |  |  |
| T1.1 Install and configure VOMS. Understand the precise semantics and current usage of groups, subgroups, roles and capabilities within VOMS applications. Find out how they are being used today for authorization decision making. Understand the relationship between the 3 default LCAS modes and the VOMS mode. Understand how this integrates into Globus Toolkit and can be integrated into OMII-UK, and its relationship with other access control mechanisms such as LCMAPS and GACLs. Document the results in D1.1 and D1.3 | 1 March 2007 | 30 June 2007 | D1.1 Requirements and information gathering D1.3 Survey of current VOMS users |  | BN, DC BN, DC |
| T1.2Production of detailed requirements for case studies utilizing VOMS, PERMIS and Shibboleth with GT4 and OMII-UK, and for GT2 based job submission systems such as Grid portals. Send questionnaire to other projects in this area to determine their requirements | 1 April | 30 July 2007 | D1.2 Use Cases to be supported |  | ALL |
| WORKPACKAGE 2: Objective: VOMS-PERMIS Integration Design | 1 April 2007 | 31 August 2007 |  |  |  |
| T2.1 Describe how VOMS and PERMIS will be integrated into GT4 for both the push and pull models |  |  | D2.1 VOMS-PERMIS integration design document (Section A) |  | BN, DC |
| T2.2.Describe how VOMS and PERMIS will be integrated into OMII-UK |  |  | D2.1 VOMS-PERMIS integration design document (Section B) |  | BN, DC |
| T2.3 Describe how VOMS and PERMIS will be integrated into GT2 and glite, and how the other components (LCAS, LCMAPS etc.) will be utilized |  |  | D2.1 VOMS-PERMIS integration design document (Section C) |  | BN, DC |
| WORKPACKAGE 3: Objective: Modify the PERMIS Policy Editor and Wizard to support VOMS policies and use case requirements | 1 July | 31 August |  |  |  |
| T3.1 Modify the PERMIS Policy Editor and Policy Wizard so that it will be easy to create policies that specify permissions based on VOMS groups, subgroups and roles. Add an Obligations window to PE and PW | 1 July | 31 August | D3.1 A modified PERMIS Policy Editor and Wizard with documentation and help files |  | BN, LLS |
| WORKPACKAGE 4: Objective: VOMS-PERMIS and Shibboleth Integration and Test-bed establishment | 1 June 2007 | 30 October 2007 |  |  |  |
| T4.1 Integrate VOMS and PERMIS into GT4 using the push mode. Build a VOMS-PERMIS PIP for extracting VOMS groups and roles ready for passing to PERMIS | 1 June | 30 June | D4.1 GT4-VOMS-PERMIS (push) Beta software ready for validation and piloting |  | BN |
| T4.2 Integrate VOMS and PERMIS into OMII according to the design produced in WP2 | 1 July | 31 July | D4.1 OMII-VOMS-PERMIS Beta software ready for validation and piloting |  | BN |
| T4.3 Integrate VOMS and PERMIS into GT2/glite according to the design produced in WP2. | 1 Aug | 31 Aug | D4.1 LCAS-VOMS-PERMIS Beta software ready for validation and piloting |  | BN, LS |
| T4.4 Integrate VOMS and PERMIS into GT4 using the pull mode. Build a PERMIS repository capable of talking to the VOMS server | 1 Sept | 30 Sept | D4.1 GT4-VOMS-PERMIS (pull) Beta software ready for validation and piloting |  | LS |
| T4.5 Prepare the infrastructure for the case studies including policy specification, Grid services, portal and portlet developments and establishment of Shibboleth IdP and SP including ensuring services run on the NGS and can access data hosted on the NGS. Look towards the Shibboleth enabling of the NGS portal and its enhancement and incorporating VOMS-PERMIS authorization scenarios. If needed adapt existing GridSphere portal solutions utilizing the Java-CoG toolkit for GT2 based job submission developed at NeSC as part of the JISC funded GLASS project | 1 June | 30 Sept | D4.2 Prepared test beds services and portals |  | RS, TD |
| T4.6 Integrate the outputs from T4.1-4 with T4.5 | 1 Oct | 30 Oct | D4.2 Completed test beds, services and portals |  | RS,BN |
| WORKPACKAGE 5: Objective: Run the Demonstrators to validate the Integration in e-Science applications | 1 Nov 2007 | 31 March 2007 |  |  |  |
| T5.1 GT4 Demonstrator of VOMS-PERMIS | 1 Nov | 30 Nov | D5.1 A paper for an international grid conference describing the piloting of the integrated VOMS-PERMIS software with GT4 and/or OMII-UK and/or LCAS |  | TD, RS |
| T5.2 OMII Demonstrator of VOMS PERMIS | 1 Dec 2007 | 15 Jan 2008 | D5.1 A paper for an international grid conference describing the piloting of the integrated VOMS-PERMIS software with GT4 and/or OMII-UK and/or LCAS |  | TD, RS |
| T5.3 GT2/glite/LCAS Demonstrator of VOMS PERMIS | 16 Jan 2008 | 28 Feb 2008 | D5.1 A paper for an international grid conference describing the piloting of the integrated VOMS-PERMIS software with GT4 and/or OMII-UK and/or LCAS. |  | TD, RS |
| T5.4 Combined demonstrator of VOMS-PERMIS, Shibboleth, GT2, GT4 and OMII-UK | 1 March | 31 March 2008 | D5.2 A paper for an international grid conference describing the piloting of the integrated authorization software utilizing Shibboleth and multiple Grid middleware (GT4 and OMII-UK) including how user single sign-on across a range of UK e-Science resources can be supported with fine grained authorisation. |  | TD, RS |
| WORKPACKAGE 6: Objective: Dissemination | 1 March 2007 | 31 July 2008 |  |  |  |
| T6.1 Build a project web site and add this to the PERMIS, NeSC and NGS web sites. | 1 March 2007 | 31 March 2007 | D6.0 Project web site |  | ALL |
| T6.2 Integrate the validated software into the NGS. | 1 April 2008 | 31 May 2008 | D6.1 The integrated software packaged with GT4 and OMII-UK and fully integrated into the NGS |  | AR |
| T6.3 Package the software along with Globus Toolkit, OMII-UK and/or NMI. Produce user friendly documentation, installation guides and tools. | 1 June | 31 July 2008 | D6.2. User, developer and administrator documentation for the integrated VOMS-PERMIS package including support in a Shibboleth-enabled environment, with guidance to Grid Operations Support Centre on practicalities of usage |  | LS, TP |
| T6.4 Project wrap up. | 1 July | 31 July 2008 | D6.3 Final report to JISC including D6.4 Document describing the overall lessons learned in supporting this infrastructure from a user, an administrator and a Grid developer perspective (this includes managers of the NGS and VO administrators wishing to utilize resources such as the NGS and end users of the NGS) |  | ALL |

Members of Project Team: BN = Bassem Nasser

LS=Linying Su

DC=David Chadwick

LLS= Lei Lei Shi

RS= Richard Sinnott

TD= Tom Doherty

AR= Andrew Richards

TP = Tim Parkinson